## Summary Dashboard
PARAKEET — TRACEABILITY MATRIX SUMMARY
Auto-calculated from Requirements Traceability sheet
Total Requirements |  | Critical Requirements
-40 |  | 14
High Priority |  | Medium Priority
10 |  | 4
In Progress |  | Planned
3 |  | 25
Phase 1 Requirements |  | Phase 2 Requirements
26 |  | 1
REQUIREMENTS BY CATEGORY
Category | # Requirements | Phase 1 | Phase 2
AI Conversation | 5 | 5 | 0
Adaptive Learning | 4 | 4 | 0
Speech & Voice | 2 | 2 | 0
Gamification | 3 | 3 | 0
Platform | 4 | 3 | 1
Monetisation | 4 | 4 | 0
Compliance | 3 | 2 | 0
Credentialing | 2 | 2 | 0
Community | 1 | 1 | 0

## Requirements Traceability
PARAKEET — REQUIREMENTS TRACEABILITY MATRIX
AI-Powered Conversational Language Learning Platform ¦ Version 1.0 ¦ February 2026 ¦ CONFIDENTIAL
REQ ID | Category | Requirement Description | Source (Charter Ref) | Priority | Deliverable | Design / Architecture | Implementation Component | Test Case ID | Acceptance Criteria | Status | Phase | Owner | Notes
REQ-001 | AI Conversation | AI conversation engine must support real-time, multi-turn dialogue | §3 Scope / §9 | Critical | AI Conversation Engine | LLM Integration Design | Node.js API + GPT-4/Claude | TC-001 | Engine responds within 10s; maintains context across ≥10 turns | In Progress | Phase 1 | CTO | Fine-tuning on language-learning corpus required
REQ-002 | AI Conversation | Contextual error correction in target language with native-language explanation | §2.3 / §3 | Critical | AI Conversation Engine | Prompt Engineering | LLM Layer | TC-002 | Corrections provided for 95%+ of grammatical errors; no conversation interruption | In Progress | Phase 1 | CTO
REQ-003 | AI Conversation | AI difficulty must adapt dynamically to real-time learner performance signals | §2.1 / §2.3 | Critical | AI Conversation Engine | Adaptive Difficulty Algorithm | LLM + Analytics Service | TC-003 | CEFR level adjusts within same session based on error rate | Planned | Phase 1 | CTO | Requires performance signal pipeline
REQ-004 | AI Conversation | Support 12 languages at launch: EN, ES, FR, DE, ZH, JA, KO, PT, IT, AR, HI, RU | §2.3 / §9 | Critical | AI Conversation Engine | Multi-language Model Config | LLM + Language Router | TC-004 | All 12 languages pass fluency QA review by native speakers | Planned | Phase 1 | CTO | Native-speaker QA mandatory per language
REQ-005 | AI Conversation | All AI conversations logged, analysed, and summarised for learner review | §2.1 | High | AI Conversation Engine | Conversation Logging Service | PostgreSQL + Analytics | TC-005 | 100% of sessions stored; summary generated within 60s of session end | Planned | Phase 1 | CTO | GDPR retention policy must govern data lifecycle
REQ-006 | Adaptive Learning | Personalised learning path generated per user using spaced-repetition logic | §2.1 / §3 | Critical | Adaptive Lesson Modules | Recommendation Engine | ML Service + PostgreSQL | TC-006 | Path generated within 30s of onboarding assessment completion | Planned | Phase 1 | Product Lead | Algorithm based on SM-2 or equivalent
REQ-007 | Adaptive Learning | System continuously re-evaluates weak areas and injects targeted micro-exercises | §2.1 | High | Adaptive Lesson Modules | Adaptive Curriculum Engine | ML Service | TC-007 | Micro-exercise injected after 3 consecutive errors on same concept | Planned | Phase 1 | Product Lead
REQ-008 | Adaptive Learning | CEFR-aligned proficiency assessments at A1–C2 levels | §2.3 / §9 | Critical | Credential Marketplace | Assessment Framework | Assessment Service | TC-008 | Assessment accurately places learners within ±1 CEFR sub-level vs. benchmark | Planned | Phase 1 | Product Lead | Validated against CEFR framework
REQ-009 | Adaptive Learning | AI-generated quizzes that evolve based on individual performance | §2.1 | Medium | Adaptive Lesson Modules | Quiz Generation Engine | LLM + Content Service | TC-009 | Quiz content refreshes every session; no identical question repeated within 7 days | Planned | Phase 1 | Product Lead
REQ-010 | Speech & Voice | Speech-to-text via OpenAI Whisper for voice conversation mode | §2.3 / §3 | Critical | Voice Mode | STT Integration | Whisper API Integration | TC-010 | STT accuracy ≥ 90% WER on target language test sets | Planned | Phase 1 | CTO | Fallback to text mode if STT unavailable
REQ-011 | Speech & Voice | Text-to-speech via AWS Polly or ElevenLabs for AI voice responses | §2.3 / §3 | Critical | Voice Mode | TTS Integration | Polly / ElevenLabs API | TC-011 | TTS latency < 2s; natural prosody rated ≥ 4/5 in UX testing | Planned | Phase 1 | CTO
REQ-012 | Gamification | Points, badges, leaderboards, and daily streak mechanics | §2.1 / §3 | High | Gamification Layer | Gamification Service | Node.js + Redis + PostgreSQL | TC-012 | All mechanics functional; streaks reset correctly at UTC midnight | Planned | Phase 1 | Product Lead
REQ-013 | Gamification | Progress dashboard with vocabulary growth, grammar accuracy, fluency score | §2.1 | High | Gamification Layer | Analytics Dashboard | React.js + Analytics API | TC-013 | Dashboard loads in < 2s; all metrics update within 5 min of session end | Planned | Phase 1 | Product Lead
REQ-014 | Gamification | Weekly and monthly AI-generated progress reports delivered via email/in-app | §4.3 | Medium | Gamification Layer | Report Generation | LLM + Email Service | TC-014 | Reports delivered within 1h of scheduled trigger; open rate tracked | Planned | Phase 1 | Product Lead
REQ-015 | Platform | React.js web application with unified learner dashboard | §2 / §3 | Critical | Web Application | Frontend Architecture | React.js | TC-015 | Core user flows complete in < 3 clicks; renders correctly on Chrome, Firefox, Safari, Edge | In Progress | Phase 1 | CTO
REQ-016 | Platform | AI response latency ≤ 10 seconds end-to-end (P95) | §2.3 / §9 | Critical | AI Conversation Engine | Performance Engineering | vLLM / TensorRT + CDN | TC-016 | P95 latency ≤ 10s under 10,000 concurrent users in load test | Planned | Phase 1 | CTO | Performance risk — mitigation in risk register
REQ-017 | Platform | Cloud infrastructure on AWS (EKS, Lambda, CloudFront) | §2.2 | High | Web Application | Cloud Architecture | AWS | TC-017 | 99.9% uptime SLA achieved in first 90 days post-launch | Planned | Phase 1 | CTO
REQ-018 | Platform | Support millions of simultaneous users with horizontal scalability | §2.2 | High | Web Application | Scalability Design | AWS EKS + Auto-scaling | TC-018 | Load test demonstrates linear scaling to 1M concurrent sessions | Planned | Phase 2 | CTO | Phase 2 scale target; Phase 1 target 100K
REQ-019 | Monetisation | Freemium tier: 3 AI conversations/week, 1 language, community access | §4.3 / §3 | Critical | Subscription System | Subscription Service | Stripe + Node.js | TC-019 | Free tier limits enforced correctly; upgrade prompt shown on limit breach | Planned | Phase 1 | CEO
REQ-020 | Monetisation | Pro tier ($14.99/mo): unlimited AI conversations, 12 languages, analytics | §4.3 | Critical | Subscription System | Subscription Service | Stripe + Node.js | TC-020 | Pro features unlocked immediately upon payment confirmation | Planned | Phase 1 | CEO
REQ-021 | Monetisation | Premium tier ($29.99/mo): Pro + advanced analytics + offline mode | §4.3 | High | Subscription System | Subscription Service | Stripe + Node.js | TC-021 | Offline mode syncs correctly on reconnect; advanced analytics render | Planned | Phase 1 | CEO | Offline mode requires service worker / caching layer
REQ-022 | Monetisation | Enterprise tier: team dashboards, custom branding, SLA support, volume pricing | §4.3 / §3 | High | Enterprise Dashboard | Enterprise Service | Node.js + Admin Portal | TC-022 | Admin dashboard displays all team members; branding config applies globally | Planned | Phase 1 | CEO
REQ-023 | Compliance | Full GDPR and CCPA compliance from Day 1 | §10 Constraints / §8 | Critical | All Components | Privacy-by-Design | All services + Legal review | TC-023 | DPA signed with all vendors; data deletion request fulfilled within 30 days | Planned | Phase 1 | CEO | Legal counsel engaged from Phase 0
REQ-024 | Compliance | Data Processing Agreements (DPAs) with all AI and cloud vendors | §10 / §8 | Critical | All Components | Vendor Compliance | Legal / Procurement | TC-024 | DPAs in place before any user data flows to vendor APIs | Planned | Phase 0 | CEO
REQ-025 | Compliance | User data retained only as long as necessary; clear deletion workflow | §10 / §8 | High | Backend / Database | Data Lifecycle Policy | PostgreSQL + Data Governance | TC-025 | Data deletion confirmed within retention policy SLA | Planned | Phase 1 | CTO
REQ-026 | Credentialing | Verifiable CEFR-aligned proficiency certificates issued post-assessment | §4.3 / §3 | High | Credential Marketplace | Credentialing Service | Assessment + PDF/Badge Service | TC-026 | Certificate generated within 5 min of passing assessment; shareable link valid for 12 months | Planned | Phase 1 | Product Lead
REQ-027 | Credentialing | Credential marketplace enabling employer/university recognition of certificates | §4.3 | Medium | Credential Marketplace | Marketplace Integration | Partner API + Backend | TC-027 | ≥ 5 employer/institution partners integrated at launch | Planned | Phase 1 | CEO | Partnership development in parallel with build
REQ-028 | Community | Built-in community and live language exchange features | §3.2 / §2.1 | Medium | Community Module | Community Service | Node.js + WebSocket | TC-028 | Users can create and join exchange sessions within 3 clicks | Planned | Phase 1 | Product Lead

## Objectives ↔ Requirements
PARAKEET — BUSINESS OBJECTIVES TO REQUIREMENTS MAPPING
Maps each charter objective to the specific requirements that deliver it
Objective ID | Objective Description | Priority | Linked Requirements | Deliverables Covered | Status
OBJ-01 | Deploy a fully functional AI conversation engine in 12 languages at launch | Critical | REQ-001, REQ-002, REQ-003, REQ-004, REQ-005, REQ-010, REQ-011 | AI Conversation Engine, Voice Mode | In Progress
OBJ-02 | Deliver adaptive lesson modules with spaced-repetition and AI personalisation | Critical | REQ-006, REQ-007, REQ-008, REQ-009 | Adaptive Lesson Modules, Credential Marketplace | Planned
OBJ-03 | Implement full gamification layer to maximise learner engagement and retention | High | REQ-012, REQ-013, REQ-014 | Gamification Layer | Planned
OBJ-04 | Launch freemium SaaS with clear Pro ($14.99) and Premium ($29.99) upgrade path | Critical | REQ-019, REQ-020, REQ-021, REQ-015, REQ-016, REQ-017 | Web Application, Subscription System | In Progress
OBJ-05 | Establish B2B enterprise sales infrastructure from Day 1 | High | REQ-022, REQ-026, REQ-027 | Enterprise Dashboard, Credential Marketplace | Planned
OBJ-06 | Achieve measurable user acquisition through organic, referral, and paid channels | High | REQ-012, REQ-013, REQ-019, REQ-028 | Gamification Layer, Community Module | Planned
OBJ-07 | Ensure full GDPR and CCPA compliance across all components from Day 1 | Critical | REQ-023, REQ-024, REQ-025 | All Components | Planned
OBJ-08 | Deliver platform latency ≤ 10s (P95) under production load | Critical | REQ-016, REQ-018 | AI Conversation Engine, Web Application | Planned

## Test Coverage
PARAKEET — TEST COVERAGE MATRIX
Maps each requirement to its test case, type, and acceptance criteria
REQ ID | Test Case ID | Test Description | Test Type | Acceptance Criteria | Priority | Expected Result | Pass / Fail
REQ-001 | TC-001 | AI Conversation Engine — Latency & Context | Performance / Functional | Responds ≤10s; maintains context across ≥10 turns | Critical | PASS | —
REQ-002 | TC-002 | Contextual Error Correction — Accuracy | Functional | ≥95% grammar errors corrected; no conversation break | Critical | PASS | —
REQ-003 | TC-003 | Adaptive Difficulty — CEFR Adjustment | Functional | CEFR level shifts within same session on signal | Critical | PASS | —
REQ-004 | TC-004 | 12-Language Fluency QA | QA / Functional | All 12 languages pass native-speaker review | Critical | PASS | —
REQ-005 | TC-005 | Conversation Logging — Completeness | Functional | 100% sessions stored; summary in ≤60s | High | PASS | —
REQ-006 | TC-006 | Personalised Learning Path — Generation Speed | Functional | Path generated ≤30s post-assessment | Critical | PASS | —
REQ-007 | TC-007 | Micro-Exercise Injection — Trigger Logic | Functional | Micro-exercise injected after 3 consecutive errors | High | PASS | —
REQ-008 | TC-008 | CEFR Assessment — Placement Accuracy | Functional | Placement within ±1 CEFR sub-level vs. benchmark | Critical | PASS | —
REQ-009 | TC-009 | Quiz Freshness — Deduplication | Functional | No identical question repeated within 7 days | Medium | PASS | —
REQ-010 | TC-010 | STT Accuracy — Whisper Integration | Integration | ≥90% WER accuracy across target languages | Critical | PASS | —
REQ-011 | TC-011 | TTS Latency & Naturalness | Integration / UX | Latency <2s; prosody rated ≥4/5 in UX test | Critical | PASS | —
REQ-012 | TC-012 | Gamification Mechanics — Streak Reset | Functional | All mechanics work; streaks reset at UTC midnight | High | PASS | —
REQ-013 | TC-013 | Progress Dashboard — Load Time | Performance | Dashboard loads ≤2s; metrics refresh ≤5 min | High | PASS | —
REQ-014 | TC-014 | AI Progress Reports — Delivery | Integration | Reports delivered within 1h of trigger | Medium | PASS | —
REQ-015 | TC-015 | Web App — Cross-Browser Compatibility | UI / Functional | Core flows in ≤3 clicks; renders on 4 browsers | Critical | PASS | —
REQ-016 | TC-016 | Platform Latency — Load Test (P95) | Performance | P95 ≤10s at 10,000 concurrent users | Critical | PASS | —
REQ-017 | TC-017 | AWS Uptime — SLA Compliance | Infrastructure | 99.9% uptime in first 90 days | High | PASS | —
REQ-018 | TC-018 | Horizontal Scalability — Load Test | Performance | Linear scaling demonstrated to 1M concurrent | High | PASS | —
REQ-019 | TC-019 | Free Tier Enforcement — Limit Logic | Functional | Limits enforced; upgrade prompt shown | Critical | PASS | —
REQ-020 | TC-020 | Pro Tier Unlock — Payment Flow | Functional | Features unlocked immediately post-payment | Critical | PASS | —
REQ-021 | TC-021 | Premium Tier — Offline Mode Sync | Functional | Offline mode syncs correctly on reconnect | High | PASS | —
REQ-022 | TC-022 | Enterprise Dashboard — Admin Controls | Functional | All team members visible; branding applies globally | High | PASS | —
REQ-023 | TC-023 | GDPR / CCPA — Data Deletion SLA | Compliance | Deletion fulfilled within 30 days of request | Critical | PASS | —
REQ-024 | TC-024 | DPA Compliance — Vendor Agreements | Compliance | DPAs in place before any user data sent to vendor | Critical | PASS | —
REQ-025 | TC-025 | Data Retention — Lifecycle Policy | Compliance | Deletion confirmed within retention policy SLA | High | PASS | —
REQ-026 | TC-026 | Credential Generation — Speed & Validity | Functional | Certificate generated ≤5 min; link valid 12 months | High | PASS | —
REQ-027 | TC-027 | Credential Marketplace — Partner Count | Integration | ≥5 employer/institution partners at launch | Medium | PASS | —
REQ-028 | TC-028 | Community Module — Session Creation UX | Functional | Exchange session created/joined in ≤3 clicks | Medium | PASS | —